## Auslastung_Prozent
Team | Engagement ID | Engagement Name | Mitarbeiter | Notizen | 24.02.2025 Feb W4 | 03.03.2025 Mar W1 | 10.03.2025 Mar W2 | 17.03.2025 Mar W3 | 24.03.2025 Mar W4 | 31.03.2025 Apr W1 | 07.04.2025 Apr W2 | 14.04.2025 Apr W3 | 21.04.2025 Apr W4 | 28.04.2025 Apr W5 | 05.05.2025 May W1 | 12.05.2025 May W2 | 19.05.2025 May W3 | 26.05.2025 May W4
AI&D - AI Consulting & Literacy | A-00000000 | Absence / Vacation / Leave | Andrea Kainz | [10 empty] | 0% | 0% | 0%
AI&D - AI Consulting & Literacy | A-00000000 | Absence / Vacation / Leave | Alexander T.
AI&D - AI Consulting & Literacy | A-00000000 | Absence / Vacation / Leave | Daniel Wielander |  | 0% |  | 0%
AI&D - AI Consulting & Literacy | E-68503880 | BA - 8. RV-SE - Los 2-5 - FY25 | Timotheus Leitner |  | 0%
AI&D - AI Consulting & Literacy | E-69542308 | OPEC_AT_AI Enablement | Janik Häußer |  | 100% | 80%
AI&D - AI Consulting & Literacy | E-69542308 | OPEC_AT_AI Enablement | Yaryna Usach |  | 80% | 80% | 60% | 60% | 60% | 60%
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Andrea Kainz | bis Ende April 20% | 80% | 60% | 20% | 20%
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Thomas Laner |  | 0% | 20%
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Benedikt |  |  | 20%
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Timotheus Leitner |  | 0%
AI&D - AI Consulting & Literacy | E-69571068 | MSFT_AT_MCI Wienerberger Copilot+Power | Thomas Laner |  | 25% | 25% | 25% | 25% | 25% | 25%
AI&D - AI Consulting & Literacy | E-69571068 | MSFT_AT_MCI Wienerberger Copilot+Power | Timotheus Leitner |  | 0%
AI&D - AI Consulting & Literacy | E-69571068 | MSFT_AT_MCI Wienerberger Copilot+Power | Yaryna Usach |  | 5% | 5% | 5% | 5% | 5% | 5%
AI&D - AI Consulting & Literacy | E-69598325 | Microsoft_AT_AT&S Copilot+Power | Janik Häußer |  |  | 10%
AI&D - AI Consulting & Literacy | E-69598325 | Microsoft_AT_AT&S Copilot+Power | Yaryna Usach |  | 5% | 5% | 15% | 15% | 15% | 15%
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Andrea |  | 10%
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Alexander T. bis 30.04. 10% |  | 10%
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Simon |  |  | 10%
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Daniel Wielander |  |  | 37.5% | 37.5% | 37.5% | 37.5% | 37.5% | 37.5% | 37.5% | 37.5% | 37.5% | 7.5%
AI&D - AI Consulting & Literacy | E-69692706 | MSFT_AT_MCI WKÖ Copilot+Power | Melissa Wang | delete booking | 0% | 0% | 80% | 80% | 64% | 80%
AI&D - AI Consulting & Literacy | E-O-10378813 | IT.NRW_RV_Beratung Statistik (Child) | Andrea Kainz | delete booking | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% |  |  | 20% | 20%
AI&D - AI Consulting & Literacy | E-O-3936991 | RV Organisations- und Personalentwicklung | Alexander Tampier |  | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
AI&D - AI Consulting & Literacy | I-TR2180009770 | MS Office Excel – EY Austria | Melissa Wang | [5 empty] | 0%
AI&D - AI Consulting & Literacy | I-TR2231062829 | Power Point Professional - EY Austria | Melissa Wang | [8 empty] | 0%
AI&D - AI Consulting & Literacy | I-TR2251293128 | Introduction to Project Management - Virtual Classroom | Andrea Kainz | [9 empty] | 0%
AI&D - AI Consulting & Literacy | I-ZZJ_2394429 | WtEY-Day GSA CNS | David Krstevski |  |  | 0%
AI&D - AI Consulting & Literacy | I-ZZJ_2394429 | WtEY-Day GSA CNS | Stefan Schmidhofer | [11 empty] | 0%
AI&D - AI Platforms & Development | A-00000000 | Absence / Vacation / Leave | Can Oezkan |  | 0%
AI&D - AI Platforms & Development | A-00000000 | Absence / Vacation / Leave | Julia Buchegger |  | 0%
AI&D - AI Platforms & Development | E-67615332 | BA - 8. RV-SE - Los 2-4 - FY24 | Tommy Tschida | extend until September with 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
AI&D - AI Platforms & Development | E-69327712 | BA - 9. RV-SE - Los 4-1 - FY26 | Benedikt Boehlke |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
AI&D - AI Platforms & Development | E-69442273 | Oper Credits_AT_Oper Projekt Support | Sean Enis Cody | Update to 70% until Mid March | 50% | 50% | 50% | 50% | 50%
AI&D - AI Platforms & Development | E-69465688 | voestgroupIT_AT_ITSMile SerceNow ImplNEW | Benedikt Boehlke | delete booking | 50% | 50% | 50% | 50% | 50%
AI&D - AI Platforms & Development | E-69465688 | voestgroupIT_AT_ITSMile SerceNow ImplNEW | Thomas Laner |  | 50% | 50% | 50% | 50% | 50% | 20%
AI&D - AI Platforms & Development | E-69576886 | MSFT_AT_MSFT-MCI AT&S Copilot | Thomas Laner |  | 15%
AI&D - AI Platforms & Development | E-69581306 | MSFT-MCI Neveon Copilot + Power | Thomas Laner |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
AI&D - AI Platforms & Development | E-69621752 | MSFT-MCI AVL Copilot+Power | Constantin Pusch |  | 50% | 59% | 59% | 59% | 59%
AI&D - AI Platforms & Development | E-O-5169596 | IKK Classic - Rahmenvertrag I Grundlaufzeit 10/24 | Constantin Pusch |  |  | 41% | 41% | 41% | 41% | 41%
AI&D - Data (enterprise, platforms) | A-00000000 | Absence / Vacation / Leave | Alexander Senne
AI&D - Data (enterprise, platforms) | A-00000000 | Absence / Vacation / Leave | Benjamin Kalusa |  | 0%
AI&D - Data (enterprise, platforms) | A-00000000 | Absence / Vacation / Leave | Regina Muehlbauer |  |  |  |  | 0%
AI&D - Data (enterprise, platforms) | E-68503880 | BA - 8. RV-SE - Los 2-5 - FY25 | Advait Athreya |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
AI&D - Data (enterprise, platforms) | E-68827273 | BA - 9. RV-SE - Los 2-1 - FY25 | Alexander Senne |  | 100% | 100% | 100% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
AI&D - Data (enterprise, platforms) | E-69220995 | IA_ESG Data Tool FY26 – EYMC | Maximilian Vallo | delete booking | 10% | 10% | 10% | 10% | 10% | 4%
AI&D - Data (enterprise, platforms) | E-69292330 | Hödlmayr_AT_Digital Transformation | Jonathan Boginski |  | 100%
AI&D - Data (enterprise, platforms) | E-69292928 | BA - 9. RV-SE - Los 1-2 - FY26 | Benjamin Kalusa |  | 0% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
AI&D - Data (enterprise, platforms) | E-69336371 | voest groupIT_AT_ITSMile-ServiceNow Impl | Regina Muehlbauer |  | 100% | 100% | 100% | 100% | 100% | 40%
AI&D - Data (enterprise, platforms) | E-69396378 | AOK AML CNS FY26 II_EXP | Maximilian Vallo | book 100% until end of May | 100% | 100% | 100% | 100% | 100% | 100%
AI&D - Data (enterprise, platforms) | E-69538164 | DE65 CNS Asklepios Dienstleistung Nov25 | Madhushree Byrappa |  | 50% | 70% | 70% | 70% | 70% | 20%
AI&D - Data (enterprise, platforms) | E-69542308 | OPEC_AT_AI Enablement | Susanne Zach |  | 5%
AI&D - Data (enterprise, platforms) | E-69590962 | Hödlmayr_AT_Digital Trans Prog Mngt Q126 | Andre Candidus |  | 0% | 0% | 0% | 0% | 0% | 0%
AI&D - Data (enterprise, platforms) | E-69590962 | Hödlmayr_AT_Digital Trans Prog Mngt Q126 | Jonathan Boginski |  |  | 100% | 100% | 100% | 100% | 25%
AI&D - Data (enterprise, platforms) | E-69624163 | AOK AML CNS FY26 III_E | Maximilian Vallo | [6 empty] | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
AI&D - Data (enterprise, platforms) | E-69629562 | HPIT_AT_IFRA UAT Koordination 1HJ2026 | Elif Deger |  | 60% | 60% | 60% | 60% | 60% | 24%
AI&D - Data (enterprise, platforms) | E-69679530 | OPEC_AT_EA Extension | Daniel Niederl | until end of June | 50% | 50% | 50% | 50% | 50% | 50%
AI&D - Data (enterprise, platforms) | E-69679530 | OPEC_AT_EA Extension | Noah Weidenhaupt |  | 100% | 100% | 100% | 100% | 100%
AI&D - Data (enterprise, platforms) | E-69716850 | EVER Neuro Pharma_AT_KI Strategie Erarb. | Andre Candidus |  | 50% | 50% | 40% | 40% | 40% | 40% | 40% | 40%
AI&D - Data (enterprise, platforms) | E-69716850 | EVER Neuro Pharma_AT_KI Strategie Erarb. | Elif Deger |  | 40% | 40% | 40% | 40% | 40%
AI&D - Data (enterprise, platforms) | I-65131897 | G_EYMC - Accounts&BusinessDev | Susanne Zach |  | 0%
AI&D - Data (enterprise, platforms) | I-O-10418070 | Dealer Dashboard Implementation | Benjamin Kalusa |  | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AI&D - Data (enterprise, platforms) | I-TR2251344365 | Deliver it Right – Global CE VC | Maximilian Vallo | [8 empty] | 0%
AI&D - Data (enterprise, platforms) | I-TR2251364214 | CNS New Engagement Manager (NEM) training - Virtual | Alexander Senne | [9 empty] | 0%
AI&D - Data (enterprise, platforms) | I-ZZJ_2394429 | WtEY-Day GSA CNS | Leo Weber |  |  | 0%
AI&D - Industrial AI | E-O-10396288 | AVL AI Support | Christoph Mayer |  | 5% | 5% | 5% | 5% | 5%
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Christian Mayr |  |  |  |  | 0%
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Laszlo Balo |  |  | 0%
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Nico Didcock | [6 empty] | 0%
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Paul Haferlbauer | [6 empty] | 0%
AI&D - AI Platforms & Development | E-69444292 | Austrotherm Agenet Entwicklung | Janik |  |  | 20%
AI&D - AI Platforms & Development | E-69680504 | Energie Steiermark | Andre |  |  |  | 10%
AI&D - AI Platforms & Development | E-69716850 | Everpharma | Melissa |  | 40% | 30% | 30%
AI&D - AI Platforms & Development | E-69730720 | Belveder Projekt | Melissa |  | 10% | 10% | 10%
AI&D - AI Platforms & Development | E-69730720 | Belveder Projekt | Andrea |  | 20% | 20%
AI&D - AI Platforms & Development | E-69680504 | Energie Steiermark | Melissa |  | 10% | 30% | 30%
AI&D - AI Platforms & Development | E-69578785 | NÖLGA | Benjamin K |  | 20% | 50%
AI&D - AI Platforms & Development | E-68941184 | EWP | Benjamin K |  |  | 50% | 50% | 50%
AI&D - AI Platforms & Development | E-68941184 | EWP | Hernan |  | 10%
AI&D - AI Consulting & Literacy | E-69542308 | OPEC Fund Enablement | Benedikt |  | 10% | 15%
AI&D - AI Platforms & Development | E-69598325 | AT&S | Benedikt |  | 10% | 10%
AI&D - AI Platforms & Development | E-68948697 | Inno Hub | Benedikt |  | 10%
AI&D - Data (enterprise, platforms) | E-69733084 | LKW Walter | Sean |  | 5% | 5%
AI&D - AI Platforms & Development | E-68698878 | Austrotherm Computer Vision | Sean |  |  | 5%
AI&D - AI Platforms & Development | E-69268842 | Austrotherm Auftragserfassung | Benedikt |  | 5% | 5%
AI&D - AI Platforms & Development | E-69581306 | Neveon | Sean |  |  |  | 50% | 50% | 50% | 50% | 50%
AI&D - AI Platforms & Development | E-68948697 | Inno Hub | Sean |  | 5%
AI&D - AI Platforms & Development | E-68948697 | Inno Hub | Moritz |  | 50% | 50%

## Auslastung_Stunden
Team | Engagement ID | Engagement Name | Mitarbeiter | Notizen | 24.02.2025 Feb W4 | 03.03.2025 Mar W1 | 10.03.2025 Mar W2 | 17.03.2025 Mar W3 | 24.03.2025 Mar W4 | 31.03.2025 Apr W1 | 07.04.2025 Apr W2 | 14.04.2025 Apr W3 | 21.04.2025 Apr W4 | 28.04.2025 Apr W5 | 05.05.2025 May W1 | 12.05.2025 May W2 | 19.05.2025 May W3 | 26.05.2025 May W4
AI&D - AI Consulting & Literacy | A-00000000 | Absence / Vacation / Leave | Andrea Kainz | [10 empty] | 0 | 0 | 0
AI&D - AI Consulting & Literacy | A-00000000 | Absence / Vacation / Leave | Alexander T.
AI&D - AI Consulting & Literacy | A-00000000 | Absence / Vacation / Leave | Daniel Wielander |  | 0 |  | 0
AI&D - AI Consulting & Literacy | E-68503880 | BA - 8. RV-SE - Los 2-5 - FY25 | Timotheus Leitner |  | 0
AI&D - AI Consulting & Literacy | E-69542308 | OPEC_AT_AI Enablement | Janik Häußer |  | 40 | 32
AI&D - AI Consulting & Literacy | E-69542308 | OPEC_AT_AI Enablement | Yaryna Usach |  | 32 | 32 | 24 | 24 | 24 | 24
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Andrea Kainz | bis Ende April 20% | 32 | 24 | 8 | 8
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Thomas Laner |  | 0 | 8
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Benedikt |  |  | 8
AI&D - AI Consulting & Literacy | E-69556342 | MSFT-MCI Spar Copilot II | Timotheus Leitner |  | 0
AI&D - AI Consulting & Literacy | E-69571068 | MSFT_AT_MCI Wienerberger Copilot+Power | Thomas Laner |  | 10 | 10 | 10 | 10 | 10 | 10
AI&D - AI Consulting & Literacy | E-69571068 | MSFT_AT_MCI Wienerberger Copilot+Power | Timotheus Leitner |  | 0
AI&D - AI Consulting & Literacy | E-69571068 | MSFT_AT_MCI Wienerberger Copilot+Power | Yaryna Usach |  | 2 | 2 | 2 | 2 | 2 | 2
AI&D - AI Consulting & Literacy | E-69598325 | Microsoft_AT_AT&S Copilot+Power | Janik Häußer |  |  | 4
AI&D - AI Consulting & Literacy | E-69598325 | Microsoft_AT_AT&S Copilot+Power | Yaryna Usach |  | 2 | 2 | 6 | 6 | 6 | 6
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Andrea |  | 4
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Alexander T. bis 30.04. 10% |  | 4
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Simon |  |  | 4
AI&D - AI Consulting & Literacy | E-69690953 | MSFT_AT_MCI WKÖ Copilot+Power | Daniel Wielander |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 3
AI&D - AI Consulting & Literacy | E-69692706 | MSFT_AT_MCI WKÖ Copilot+Power | Melissa Wang | delete booking | 0 | 0 | 32 | 32 | 25.6 | 32
AI&D - AI Consulting & Literacy | E-O-10378813 | IT.NRW_RV_Beratung Statistik (Child) | Andrea Kainz | delete booking | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8
AI&D - AI Consulting & Literacy | E-O-3936991 | RV Organisations- und Personalentwicklung | Alexander Tampier |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
AI&D - AI Consulting & Literacy | I-TR2180009770 | MS Office Excel – EY Austria | Melissa Wang | [5 empty] | 0
AI&D - AI Consulting & Literacy | I-TR2231062829 | Power Point Professional - EY Austria | Melissa Wang | [8 empty] | 0
AI&D - AI Consulting & Literacy | I-TR2251293128 | Introduction to Project Management - Virtual Classroom | Andrea Kainz | [9 empty] | 0
AI&D - AI Consulting & Literacy | I-ZZJ_2394429 | WtEY-Day GSA CNS | David Krstevski |  |  | 0
AI&D - AI Consulting & Literacy | I-ZZJ_2394429 | WtEY-Day GSA CNS | Stefan Schmidhofer | [11 empty] | 0
AI&D - AI Platforms & Development | A-00000000 | Absence / Vacation / Leave | Can Oezkan |  | 0
AI&D - AI Platforms & Development | A-00000000 | Absence / Vacation / Leave | Julia Buchegger |  | 0
AI&D - AI Platforms & Development | E-67615332 | BA - 8. RV-SE - Los 2-4 - FY24 | Tommy Tschida | extend until September with 80% | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
AI&D - AI Platforms & Development | E-69327712 | BA - 9. RV-SE - Los 4-1 - FY26 | Benedikt Boehlke |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
AI&D - AI Platforms & Development | E-69442273 | Oper Credits_AT_Oper Projekt Support | Sean Enis Cody | Update to 70% until Mid March | 20 | 20 | 20 | 20 | 20
AI&D - AI Platforms & Development | E-69465688 | voestgroupIT_AT_ITSMile SerceNow ImplNEW | Benedikt Boehlke | delete booking | 20 | 20 | 20 | 20 | 20
AI&D - AI Platforms & Development | E-69465688 | voestgroupIT_AT_ITSMile SerceNow ImplNEW | Thomas Laner |  | 20 | 20 | 20 | 20 | 20 | 8
AI&D - AI Platforms & Development | E-69576886 | MSFT_AT_MSFT-MCI AT&S Copilot | Thomas Laner |  | 6
AI&D - AI Platforms & Development | E-69581306 | MSFT-MCI Neveon Copilot + Power | Thomas Laner |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AI&D - AI Platforms & Development | E-69621752 | MSFT-MCI AVL Copilot+Power | Constantin Pusch |  | 20 | 23.6 | 23.6 | 23.6 | 23.6
AI&D - AI Platforms & Development | E-O-5169596 | IKK Classic - Rahmenvertrag I Grundlaufzeit 10/24 | Constantin Pusch |  |  | 16.4 | 16.4 | 16.4 | 16.4 | 16.4
AI&D - Data (enterprise, platforms) | A-00000000 | Absence / Vacation / Leave | Alexander Senne
AI&D - Data (enterprise, platforms) | A-00000000 | Absence / Vacation / Leave | Benjamin Kalusa |  | 0
AI&D - Data (enterprise, platforms) | A-00000000 | Absence / Vacation / Leave | Regina Muehlbauer |  |  |  |  | 0
AI&D - Data (enterprise, platforms) | E-68503880 | BA - 8. RV-SE - Los 2-5 - FY25 | Advait Athreya |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
AI&D - Data (enterprise, platforms) | E-68827273 | BA - 9. RV-SE - Los 2-1 - FY25 | Alexander Senne |  | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
AI&D - Data (enterprise, platforms) | E-69220995 | IA_ESG Data Tool FY26 – EYMC | Maximilian Vallo | delete booking | 4 | 4 | 4 | 4 | 4 | 1.6
AI&D - Data (enterprise, platforms) | E-69292330 | Hödlmayr_AT_Digital Transformation | Jonathan Boginski |  | 40
AI&D - Data (enterprise, platforms) | E-69292928 | BA - 9. RV-SE - Los 1-2 - FY26 | Benjamin Kalusa |  | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
AI&D - Data (enterprise, platforms) | E-69336371 | voest groupIT_AT_ITSMile-ServiceNow Impl | Regina Muehlbauer |  | 40 | 40 | 40 | 40 | 40 | 16
AI&D - Data (enterprise, platforms) | E-69396378 | AOK AML CNS FY26 II_EXP | Maximilian Vallo | book 100% until end of May | 40 | 40 | 40 | 40 | 40 | 40
AI&D - Data (enterprise, platforms) | E-69538164 | DE65 CNS Asklepios Dienstleistung Nov25 | Madhushree Byrappa |  | 20 | 28 | 28 | 28 | 28 | 8
AI&D - Data (enterprise, platforms) | E-69542308 | OPEC_AT_AI Enablement | Susanne Zach |  | 2
AI&D - Data (enterprise, platforms) | E-69590962 | Hödlmayr_AT_Digital Trans Prog Mngt Q126 | Andre Candidus |  | 0 | 0 | 0 | 0 | 0 | 0
AI&D - Data (enterprise, platforms) | E-69590962 | Hödlmayr_AT_Digital Trans Prog Mngt Q126 | Jonathan Boginski |  |  | 40 | 40 | 40 | 40 | 10
AI&D - Data (enterprise, platforms) | E-69624163 | AOK AML CNS FY26 III_E | Maximilian Vallo | [6 empty] | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
AI&D - Data (enterprise, platforms) | E-69629562 | HPIT_AT_IFRA UAT Koordination 1HJ2026 | Elif Deger |  | 24 | 24 | 24 | 24 | 24 | 9.6
AI&D - Data (enterprise, platforms) | E-69679530 | OPEC_AT_EA Extension | Daniel Niederl | until end of June | 20 | 20 | 20 | 20 | 20 | 20
AI&D - Data (enterprise, platforms) | E-69679530 | OPEC_AT_EA Extension | Noah Weidenhaupt |  | 40 | 40 | 40 | 40 | 40
AI&D - Data (enterprise, platforms) | E-69716850 | EVER Neuro Pharma_AT_KI Strategie Erarb. | Andre Candidus |  | 20 | 20 | 16 | 16 | 16 | 16 | 16 | 16
AI&D - Data (enterprise, platforms) | E-69716850 | EVER Neuro Pharma_AT_KI Strategie Erarb. | Elif Deger |  | 16 | 16 | 16 | 16 | 16
AI&D - Data (enterprise, platforms) | I-65131897 | G_EYMC - Accounts&BusinessDev | Susanne Zach |  | 0
AI&D - Data (enterprise, platforms) | I-O-10418070 | Dealer Dashboard Implementation | Benjamin Kalusa |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AI&D - Data (enterprise, platforms) | I-TR2251344365 | Deliver it Right – Global CE VC | Maximilian Vallo | [8 empty] | 0
AI&D - Data (enterprise, platforms) | I-TR2251364214 | CNS New Engagement Manager (NEM) training - Virtual | Alexander Senne | [9 empty] | 0
AI&D - Data (enterprise, platforms) | I-ZZJ_2394429 | WtEY-Day GSA CNS | Leo Weber |  |  | 0
AI&D - Industrial AI | E-O-10396288 | AVL AI Support | Christoph Mayer |  | 2 | 2 | 2 | 2 | 2
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Christian Mayr |  |  |  |  | 0
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Laszlo Balo |  |  | 0
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Nico Didcock | [6 empty] | 0
AI&D - Industrial AI | I-ZZJ_2394429 | WtEY-Day GSA CNS | Paul Haferlbauer | [6 empty] | 0
Zusaetzliche Buchungen | E-69444292 | Austrotherm Agenet Entwicklung | Janik |  |  | 8
Zusaetzliche Buchungen | E-69680504 | Energie Steiermark | Andre |  |  |  | 4
Zusaetzliche Buchungen | E-69716850 | Everpharma | Melissa |  | 16 | 12 | 1200
Zusaetzliche Buchungen | E-69730720 | Belveder Projekt | Melissa |  | 4 | 4 | 4
Zusaetzliche Buchungen | E-69730720 | Belveder Projekt | Andrea |  | 8 | 8
Zusaetzliche Buchungen | E-69680504 | Energie Steiermark | Melissa |  | 4 | 12 | 12
Zusaetzliche Buchungen | E-69578785 | NÖLGA | Benjamin K |  | 8 | 20
Zusaetzliche Buchungen | E-68941184 | EWP | Benjamin K |  |  | 20 | 20 | 20
Zusaetzliche Buchungen | E-68941184 | EWP | Hernan |  | 4
Zusaetzliche Buchungen | E-69542308 | OPEC Fund Enablement | Benedikt |  | 4 | 6
Zusaetzliche Buchungen | E-69598325 | AT&S | Benedikt |  | 4 | 4
Zusaetzliche Buchungen | E-68948697 | Inno Hub | Benedikt |  | 4
Zusaetzliche Buchungen | E-69733084 | LKW Walter | Sean |  | 2 | 2
Zusaetzliche Buchungen | E-68698878 | Austrotherm Computer Vision | Sean |  |  | 2
Zusaetzliche Buchungen | E-69268842 | Austrotherm Auftragserfassung | Benedikt |  | 2 | 2
Zusaetzliche Buchungen | E-69581306 | Neveon | Sean |  |  |  | 20 | 20 | 20 | 20 | 20
Zusaetzliche Buchungen | E-68948697 | Inno Hub | Sean |  | 2
Zusaetzliche Buchungen | E-68948697 | Inno Hub | Moritz |  | 20 | 20

## Mitarbeiter_Uebersicht
Mitarbeiter | Team(s) | 24.02.2025 Feb W4 (%) | 24.02.2025 Feb W4 (Std) | 03.03.2025 Mar W1 (%) | 03.03.2025 Mar W1 (Std) | 10.03.2025 Mar W2 (%) | 10.03.2025 Mar W2 (Std) | 17.03.2025 Mar W3 (%) | 17.03.2025 Mar W3 (Std) | 24.03.2025 Mar W4 (%) | 24.03.2025 Mar W4 (Std) | 31.03.2025 Apr W1 (%) | 31.03.2025 Apr W1 (Std) | 07.04.2025 Apr W2 (%) | 07.04.2025 Apr W2 (Std) | 14.04.2025 Apr W3 (%) | 14.04.2025 Apr W3 (Std) | 21.04.2025 Apr W4 (%) | 21.04.2025 Apr W4 (Std) | 28.04.2025 Apr W5 (%) | 28.04.2025 Apr W5 (Std) | 05.05.2025 May W1 (%) | 05.05.2025 May W1 (Std) | 12.05.2025 May W2 (%) | 12.05.2025 May W2 (Std) | 19.05.2025 May W3 (%) | 19.05.2025 May W3 (Std) | 26.05.2025 May W4 (%) | 26.05.2025 May W4 (Std)
Advait Athreya | AI&D - Data (enterprise, platforms) | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40
Alexander Senne | AI&D - Data (enterprise, platforms) | 100% | 40 | 100% | 40 | 100% | 40 | 80% | 32 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40
Alexander T. | AI&D - AI Consulting & Literacy
Alexander T. bis 30.04. 10% | AI&D - AI Consulting & Literacy | 10% | 4
Alexander Tampier | AI&D - AI Consulting & Literacy | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32
Andre | Zusaetzliche Buchungen |  |  |  |  | 10% | 4
Andre Candidus | AI&D - Data (enterprise, platforms) | 50% | 20 | 50% | 20 | 40% | 16 | 40% | 16 | 40% | 16 | 40% | 16 | 40% | 16 | 40% | 16
Andrea | AI&D - AI Consulting & Literacy, Zusaetzliche Buchungen | 30% | 12 | 20% | 8
Andrea Kainz | AI&D - AI Consulting & Literacy | 100% | 40 | 80% | 32 | 40% | 16 | 40% | 16 | 20% | 8 | 20% | 8 | 20% | 8 | 20% | 8 | 20% | 8 | 20% | 8 |  |  |  |  | 20% | 8 | 20% | 8
Benedikt | AI&D - AI Consulting & Literacy, Zusaetzliche Buchungen | 35% | 14 | 50% | 20
Benedikt Boehlke | AI&D - AI Platforms & Development | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20
Benjamin K | Zusaetzliche Buchungen | 20% | 8 | 100% | 40 | 50% | 20 | 50% | 20
Benjamin Kalusa | AI&D - Data (enterprise, platforms) | 20% | 8 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32
Can Oezkan | AI&D - AI Platforms & Development
Christian Mayr | AI&D - Industrial AI
Christoph Mayer | AI&D - Industrial AI | 5% | 2 | 5% | 2 | 5% | 2 | 5% | 2 | 5% | 2
Constantin Pusch | AI&D - AI Platforms & Development | 50% | 20 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 41% | 16.4
Daniel Niederl | AI&D - Data (enterprise, platforms) | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20
Daniel Wielander | AI&D - AI Consulting & Literacy |  |  | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 37.5% | 15 | 7.5% | 3
David Krstevski | AI&D - AI Consulting & Literacy
Elif Deger | AI&D - Data (enterprise, platforms) | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 24% | 9.6
Hernan | Zusaetzliche Buchungen | 10% | 4
Janik | Zusaetzliche Buchungen |  |  | 20% | 8
Janik Häußer | AI&D - AI Consulting & Literacy | 100% | 40 | 90% | 36
Jonathan Boginski | AI&D - Data (enterprise, platforms) | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 25% | 10
Julia Buchegger | AI&D - AI Platforms & Development
Laszlo Balo | AI&D - Industrial AI
Leo Weber | AI&D - Data (enterprise, platforms)
Madhushree Byrappa | AI&D - Data (enterprise, platforms) | 50% | 20 | 70% | 28 | 70% | 28 | 70% | 28 | 70% | 28 | 20% | 8
Maximilian Vallo | AI&D - Data (enterprise, platforms) | 110% | 44 | 110% | 44 | 110% | 44 | 110% | 44 | 110% | 44 | 164% | 65.6 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40
Melissa | Zusaetzliche Buchungen | 60% | 24 | 70% | 28 | 3040% | 1216
Melissa Wang | AI&D - AI Consulting & Literacy |  |  |  |  | 80% | 32 | 80% | 32 | 64% | 25.6 | 80% | 32
Moritz | Zusaetzliche Buchungen | 50% | 20 | 50% | 20
Nico Didcock | AI&D - Industrial AI
Noah Weidenhaupt | AI&D - Data (enterprise, platforms) | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40
Paul Haferlbauer | AI&D - Industrial AI
Regina Muehlbauer | AI&D - Data (enterprise, platforms) | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 40% | 16
Sean | Zusaetzliche Buchungen | 10% | 4 | 10% | 4 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20
Sean Enis Cody | AI&D - AI Platforms & Development | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20 | 50% | 20
Simon | AI&D - AI Consulting & Literacy |  |  | 10% | 4
Stefan Schmidhofer | AI&D - AI Consulting & Literacy
Susanne Zach | AI&D - Data (enterprise, platforms) | 5% | 2
Thomas Laner | AI&D - AI Consulting & Literacy, AI&D - AI Platforms & Development | 100% | 40 | 105% | 42 | 85% | 34 | 85% | 34 | 85% | 34 | 55% | 22 | 10% | 4 | 10% | 4 | 10% | 4 | 10% | 4
Timotheus Leitner | AI&D - AI Consulting & Literacy
Tommy Tschida | AI&D - AI Platforms & Development | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40 | 100% | 40
Yaryna Usach | AI&D - AI Consulting & Literacy | 90% | 36 | 90% | 36 | 80% | 32 | 80% | 32 | 80% | 32 | 80% | 32